Draft FSHDPII Time line for the Next Steps

| S/N | Activity | Purpose | Responsible/support | Date | Output | Target audience/ participants |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Briefing of the Directors and CEOs of Agencies and Parastatals | Ownership of plan | Heads of Planning Cells of DAPs | August | Plan development understood and commitment obtained on the process. | Heads of DAP |
| 2 | Internal meetings of programme managers within the DAPs | Advocacy and consensus building | Planning Cell members | August | Common understanding of roles and responsibilities and need for coordination | FMOH Depts, Agencies and Parastatals expanded Planning Cells |
| 3 | Data Collection for SITAN and plan development | Plan development process | Planning Cell members of DAPs | August-September | Data for development of SITAN and organization’s Plan collected | DAPs |
| 4 | Development of Situation Analysis for the FSHDPII | Plan development process | Federal Consultants | September | SITAN for FSHDPII developed |  |
| 5 | Planning Meeting for the FSHDPII, M&E and HRH Profile | Plan development process | National & Federal Consultants, and NSHDP Secretariat (FMOH) | September | Draft FSHDPII with the HRH Profile and M&E Plan developed | Planning Cell members of DAPs |
|  | Costing of the Federal Plan | Plan development process | National and Federal Costing Consultants | September | Costed FSHDPII | Planning Cell members of DAPs |
|  |  | Plan development process | Federal and National Consultants | September |  | M&E Officers and HRH Officers of DAPs |
|  | Development of 2018 Operational Plans | Plan implementation | Federal Consultants and Planning Cell members DAPs | September | 2018 results focused Operational Plan developed | Planning Cell members and Programme Managers of DAPs |
|  | Pre-Validation Meeting | Ownership | Federal Consultants and Heads of Planning Cells in DAPs | September | Draft Plan presented to DAPs focused 2018 Operational Plans |  |
|  | Validation Meeting | Ownership | National, Federal Consultants and FMOH Secretariat | October | Training for state and LGA personnel on the MTSS and 2010 results-focused operational plans | HMH, HMSH, PSH, all CEOs of DAPs and Heads of Planning Cells, FMOH key Programme Managers and DPs |
|  | Finalization and Submission of the FSHDPII | Ownership | Federal Consultants | October |  | FMOH Secretariat and National Consultants |